REQUEST

to participate in the competition for grant funding

for scientific and (or) scientific and technical projects for 2023-2025

1. Abstract

The past fills the future. The data obtained from the results of the conducted research can become the basis for the formation of Kazakhstani patriotism, the development and preservation of the cultural code of the nation.

The main problem of the modern society of Kazakhstan is the low level of knowledge, and hence the lack of interest in the cultural and historical objects of their homeland. The current state of museums requires the use of modern technologies. In addition to the digitalization of historical documents and their transfer to electronic media, it is already possible to digitize the still undestroyed sacred and cultural-historical objects of the northern region of Kazakhstan.

The goal of the project is to increase the level of knowledge and preserve the cultural and historical heritage of Northern Kazakhstan, through the use of digital three-dimensional technologies.

As part of the Digital Kazakhstan program, it is necessary to introduce new digital technologies into all spheres of life. For the correct formation of patriotism among the younger generation, cultural and historical objects accessible for study are required, which will allow researchers to obtain information that objectively reflects the main milestones in the development of the country and people.

The main idea of the project is the creation of a digital repository of cultural and historical objects of Northern Kazakhstan. Open access to such a database will give a wide range of people to get acquainted, study and explore the history of our people. Visualized and scaled cultural and historical objects will become accessible to people with disabilities around the world. Thanks to 3D technologies, Kazakh and foreign researchers will be able to obtain accurate scaled copies of famous cultural and historical objects of Northern Kazakhstan.

The main research approach includes the following steps:

- compiling a catalog of historical objects that are in an unsatisfactory condition and require priority digitization for their preservation;

- laser three-dimensional scanning of large cultural and historical monuments using a quadrocopter;

- rendering of the resulting 3D models, i.e. their refinement and creation of high-quality and reliable three-dimensional digital cultural and historical objects in the 3Ds Max program;

- scaling and three-dimensional printing of the obtained prototypes.

The project is timely and relevant. The results obtained can be used in the course of studying historical disciplines in secondary and higher educational institutions.

The research methodology is an update of historical informatics, through the introduction of digitalization through three-dimensional technologies. In general, the project will make it possible to obtain digital copies of famous cultural and historical objects of Northern Kazakhstan and print their reduced copies on a three-dimensional printer.

The resulting database of digital cultural and historical objects of Northern Kazakhstan can become the basis for museum exhibits throughout the Republic. In addition, it can make it possible to track the degree of wear and destruction of sacred historical monuments.

Based on the results of the research, it is planned to publish two articles in journals with a high impact factor indexed in the Web of Science databases (opportunities for additive technologies) and Scopus, which has a CiteScore percentile in the Scopus database of at least 35 (thirty-five) (preservation of historical heritage); also two articles in domestic publications recommended by the KOKSNVO; defend a master's thesis; publish one collective monograph and collect enough material for the subsequent development of a textbook on the information history of the northern region of Kazakhstan.

The foundations for the formation of a single cultural space of Kazakhstan will be laid on the basis of digitized cultural and historical objects and museum funds of Northern Kazakhstan.

The study and preservation of the heritage of ancestors will provide an opportunity to unlock the potential of the Northern region as an additional factor in the country's economic growth.

It is also possible to use digitized three-dimensional models for the manufacture of teaching aids and souvenirs.

The created database of digitally visualized cultural and historical objects of Northern Kazakhstan can become an export item for the museums of the world.

Regional akimats of the northern regions of Kazakhstan, the Ministry of Information and Social Development of the Republic of Kazakhstan, government agencies and authorized bodies related to the preservation of cultural and historical objects are interested in the results of the project.

2. Explanatory note

1. General information

1.1. THREE-DIMENSIONAL TECHNOLOGIES IN THE PROCESS OF PRESERVING THE CULTURAL AND HISTORICAL HERITAGE OF NORTHERN KAZAKHSTAN

1.2. The name of the priority direction of the development of science - Research in the field of social sciences and humanities

1.3. Name of the specialized scientific direction - 7.2 Fundamental, applied, interdisciplinary research in the field of the humanities: - 7.2.10 Information and digital technologies in the socio-humanitarian sphere. Man in the information space.

Field of research - social and human sciences, MRNTI 03.20.00

Type of research - applied

1.4. The expected start and end date of the project is February 1, 2023, the end is December 30, 2025, the duration of the program is 35 months.

1.5. The requested amount of grant funding for the entire duration of the program is 50,000 thousand tenge (fifty million tenge) and by years: 2023 - 19,180 thousand tenge, 2024 - 17,500 thousand tenge, 2025 - 13,320 thousand tenge.

1.6. Key words: digitalization of cultural and historical heritage, 3D scanning, 3D modeling, 3D printing, history, archiving.

2. General concept of the project

2.1. Introductory part.

The state task of forming national self-consciousness is aimed at using digital technologies that can harmoniously fit into the modern space of preserving historical memory, and digital three-dimensional reconstruction for the preservation of cultural heritage will make historical facts accessible to a wide range of people. The creation of a database of digital cultural and historical objects will make available historiographic material on Northern Kazakhstan for a wide range of interested parties, as well as for students of secondary and higher schools.

The project will improve the effectiveness of scientific developments and ensure integration into the global scientific space. Thanks to WEB-technologies, everyone will be able to get access to the cultural and historical sites of Northern Kazakhstan.

2.2 The goal of the project is to increase the level of knowledge and preserve the cultural and historical heritage of Northern Kazakhstan, through the use of digital three-dimensional technologies.

2.3 Project objectives:

In accordance with the goal, it is necessary to solve the following tasks:

2.3.1 - compiling a catalog of historical objects that are in an unsatisfactory condition and require priority digitization for their preservation;

Activities: work with available information and search for data on the state of cultural and historical objects. Trips to the regions of Northern Kazakhstan. Processing of statistical data. Analytical work.

Expected result: publication of articles and development of recommendations for government agencies at all levels involved in the preservation of historical monuments.

2.3.2 - three-dimensional laser scanning of large cultural and historical monuments using a quadrocopter;

Activities: Acquiring and working with a 3D scanner and a quadcopter. Processing of statistical data. Analytical work.

Expected result: publication of articles and preparatory work on compiling a digital database of cultural and historical objects of Northern Kazakhstan.

2.3.3 - rendering of the obtained 3D models, i.e. their refinement and creation of high-quality and reliable three-dimensional digital cultural and historical objects in the 3Ds Max program;

2.3.4 - scaling and three-dimensional printing of the obtained prototypes.

As a result of the fulfillment of the tasks set, it will be possible to realize the high potential of cultural openness of Kazakhstan by creating a virtual repository with digital information of natural landscape monuments and cultural heritage of the Northern region of Kazakhstan;

There will be an advanced innovative infrastructure for research, digital conservation and restoration of cultural and historical heritage;

The monitoring of the state of historical and cultural monuments of Northern Kazakhstan using advanced technological achievements will give a real picture for planning restoration work;

Three-dimensional miniature copies of historical objects will be made available to the blind and visually impaired, which will improve their quality of life.

In general, the replenishment and systematization of the cultural and historical collections of Northern Kazakhstan and the creation of a special repository on the basis of the National Museum of the Republic of Kazakhstan will give impetus to the promotion and popularization of the material and spiritual heritage of the Kazakhs.

3. Scientific novelty and significance of the program

The scientific novelty of the project lies in the creation of a database of digitized cultural and historical objects of Northern Kazakhstan, available for detailed study and preservation in their original form. For the first time, the study will use 3D scanning technologies, rendering (recreation) and 3D printing of cultural and historical objects on a scale.

For historical analysis and scientific research, there are already a large number of digitized documents that are in the public domain or have already been published in strictly scientific publications.

Almost every European country has created digitized historical collections. But the digitalization of historical documentary materials has, in addition to a positive effect, also negative aspects. Only certain documents with a political and social orientation were preserved [1].

Creation of 3D models of real objects will allow preserving these objects as a cultural heritage for research. Also for reconstruction, restoration, analysis and visualization. The created three-dimensional model guarantees high geometric accuracy of dimensions, shapes and arrangements, provides an overview and accessibility of all details.

Kazakhstan should become the central digital hub in a significant part of the Eurasian region [2]. Global digitalization is not far off. Collection of information, its analysis and processing is impossible without new technologies. Interactive maps for tourists, students, and businessmen have been around for a long time and are constantly being improved. Digitalization is an objective reality and an integral part of our life [3].

The created database of digital objects of history will increase the possibility of using new concepts in research projects, identifying promising areas for the application of mathematical methods and digital technologies in historical research.

As a specific property of digital products that distinguishes them from other information products, we should mention the possibility of their transmission over communication channels without loss of accuracy, cloning instead of copying when rewriting, as well as the possibility of visualization through three-dimensional printing [4].

Digital solutions are reliable, scalable and virtually indestructible (with the right choice of backup options). The project is fully consistent with the state program "Digital Kazakhstan".

The project was developed in accordance with the Law of the Republic of Kazakhstan "On the protection and use of objects of historical and cultural heritage" No. 288-VІ ZRK

The state task - the formation of national self-consciousness, is aimed at the use of digital technologies that will make available historiographic material on Northern Kazakhstan for a wide range of interested persons, as well as students of secondary and higher schools. This can contribute to the formation of patriotism and will give a more complete picture of the historical process or event being studied. Which, in turn, can give a heuristic impetus to the generation of a new research hypothesis or correct the conclusions of some already completed studies.

The project is interdisciplinary in nature and, in addition to new historical facts, will provide material for research on historical informatics and improvement of technological parameters when scanning large geographical objects or small objects of Kazakh culture in three dimensions.

Today the world is losing cultural and historical monuments faster than they can be digitized [5]. As mentioned above, it will be possible to improve the quality of life of visually impaired or blind people who will be able to explore cultural and historical objects made on 3D printers by touch. The printout can be realistic or scaled, but without loss of accuracy. The combination of digital information obtained using drones, then 3D modeling and 3D printing of historical objects to scale has not yet been used in Kazakhstan.

The prerequisites for the implementation of the program are the "History-Oriented Information Systems" system on the DigitalHistory.ru portal, developed at the Center for Digital Humanities of the Perm State National Research University. Research work on the creation of the foundations for the integration of digital cultural heritage information resources and the process of building digital cultural heritage infrastructures is essential. The well-known expert Antonello Fres emphasizes the particular relevance of the introduction of three-dimensional technologies for European digital historical and cultural heritage. Approaches to 3D digitization of cultural and historical objects are described in the works of Nikolai Stoymenov, Petr Panev, Miglen Panev, Dimitar Karastoyanov [6]. A great merit belongs to the laboratory of the Institute of Information and Communication Technologies of the Bulgarian Academy of Sciences.

To date, there are virtual historical reconstructions abroad, there are not many of them, the largest of them are:

- In Portugal - virtual reconstructions of the Cistercian monastery of Santa Maria of the 16th century;

- In Spain, the city of Ripoll - the reconstruction of the monastery of Santa Maria XII century;

- In France - the reconstruction of the monastery of Saint-Avi Senier XII century;

- In Hungary - the reconstruction of the Cistercian monastery of the XII century;

- In Turkey - the reconstruction of the monastery of Christ Pantepopt XI century.

Research using three-dimensional technologies in the field of historical reconstruction is known at the liberal arts departments of the US universities (Brown, Harvard, Columbia, Stanford), the University of California UCLA, the Institute of Advanced Technologies in the Humanities of the University of Virginia, in the UK universities (University of Birmingham, King's College London), as well as France, Italy, Spain, Austria and other countries [6].

All known digital historical monuments were created in various programs, and not all and not always have the opportunity to use these reconstructions for research, their cost is considerable. invested a lot of labor and cost. The first publications on the use of 3D modeling technologies in historical research date back to 2010 (Yu. M. Baranov, E. A. Kurlaev). A significant impact on the spread of the introduction of 3D modeling technologies in the field of historical research was exerted by the activities of the Russian Association "History and Computer" (AIK). Since 2016, there have been works on the virtual reconstruction of historians of the Tambov State University (R.B. Konchakov, D.I. Zherebyatiev), the Faculty of Arts of St. Petersburg State University in collaboration with the Institute of the History of Material Culture of the Russian Academy of Sciences (E.V. Logdacheva, S.V. Shvemberger and others), Siberian Federal University (M. V. Rumyantsev, A. A. Smolin, I. N. Rudov, N. O. Pikov), Ural Pedagogical University (A. V. Fishchev) [7].

As for Kazakhstan, within the framework of the Sacred Kazakhstan project, in 2018, the LANIT-Integration group digitized 13 historical objects with photorealistic quality, including the majestic Mausoleum of Khoja Ahmed Yasawi, recognized as a UNESCO World Heritage Site. Recreated in digital form, the objects are transferred to the virtual space, but the created models cannot be launched for 3D printing. digitalization was not carried out with the necessary parameters.

For this project, the publications of the members of the research group and completed initiative topics can be considered as a backlog: 1) registration number 0115RKI02087 Creation of a design and 3D modeling center, closing date 2018; 2) registration number 0118RKI0029 "Introduction of digital technologies into the work of the design and 3D modeling center", closing date 2021.

The significance of the project. Digital cultural and historical heritage will expand economic, social and cultural international interaction.

Free online access to the digitized cultural and historical objects of Kazakhstan will make the Kazakh people and their history world-famous.

4. Research methods and ethical issues

Digitization and three-dimensional reconstruction for the preservation of cultural and historical heritage can be performed by several methods: the use of digital photogrammetry or direct measurement and CAD methods, orthophotography of the surface. Highly detailed 3D reconstruction by a laser scanner and the integration of image-based modeling together with photogrammetry are well known in world practice, for example, the Church of Santo Domingo (Portugal).

When rendering digital models, it is planned to use the licensed computer-aided design system KOMPAS 3D V18, 3Ds Max and SolidWorks, as well as Blender.

Initial 3D models are planned to be captured on a digital camera using a drone. Further refinement of the data obtained by a 3D scanner, and after rendering, analysis and systematization of cultural and historical objects of Northern Kazakhstan will take place.

The plan is to use the scanner on Solid Edge software, which includes the option to connect triangular mesh objects and solid models without complex and error-prone transformations.

Three-dimensional laser scanning creates high-precision three-dimensional models with the possibility of their refinement and transfer to any digital communication device. A 3D model consists of a large number of points that precisely define the geometry of an object. In addition, to obtain a realistic appearance of the model, texture maps obtained from a high-resolution digital camera are required.

Methods for collecting primary (initial) information are field work that includes scanning of each object and full photographic coverage for photogrammetry and phototexturing tasks. The optimal combination of techniques will depend on various parameters: overall dimensions, shape, texture, condition of the object, etc.

For qualitative research and monitoring of the state of the historical object, three-dimensional printing is supposed. It is planned to use an inexpensive 3D printer that uses additive FDM technology. This is a printer for printing large models with low shrinkage plastics, including PLA, PETG, ASA, glass-filled and carbon-filled composites, etc.

The Project will ensure compliance with the principles of scientific ethics, i. ethical management procedures, in particular, maintaining high standards of intellectual honesty and avoiding the fabrication of scientific data, falsification, plagiarism, false co-authorship, use by individual participants of collective research, data and conclusions obtained in research, without the consent of other participants.

The conditions for registration and division of intellectual property rights to the results of the study will correspond to the methods of protecting intellectual property in accordance with the legislation of the Republic of Kazakhstan.

5. Research team and project management

Project leader - Mukhamadeeva I. A. - Ph.D., professor of KU named after A. Myrzakhmetov, scientific and pedagogical experience is more than 25 years, more than 80 publications in Kazakhstani and foreign scientific journals, including 5 impact factor, in the materials of republican and international scientific conferences. Author of 5 monographs and a number of textbooks and e-learning tools on the EP "History" and "International Relations" (8 copyright certificates), head of diploma and master's projects on the history of Kazakhstan, Hirsch index - 2, Researcher ID Web of Science: AHH-1048 -2022, Scopus ID 57207822681. ORSID - https://orcid.org/0000-0003-0590-0756.

The duties, as the head of the program, will include the selection, analysis and systematization of cultural and historical objects of Northern Kazakhstan, work with regional museum collections and guidance of undergraduates in the chosen direction.

The main publications of the head of the research group Mukhamadeeva I.A.

| № | Title of the publication | Year of publication, magazine | Publication status |
| --- | --- | --- | --- |
| 1 | Structural and Logical Approach to the Introduction of Dual Training in Vocational and Technical Education System of the Republic of Kazakhstan | Indian Journal of Science and Technology, Vol 8(S10), DOI: 10.17485/ijst/2015/v8iS10/84854, December 2015. – Р. 239-246. Cite Score 2015 IF: 1,0, https://indjst.org/articles/structural-and-logical-approach-to-the-introduction-of-dual-training-in-vocational-and-technical-education-system-of-the-republic-of-kazakhstan Процентиль – 60 | Scopus |
| 2 | Mechanisms on improving the Education System Quality in the Republic of Kazakhstan | Journal-of-intellectual-Disability-Diagnosis and Treatmen, 2018,6, 119-124. http://www.lifescienceglobal.com/journals/journal-of-intellectual-disability-diagnosis-and-treatment Процентиль – 31 | Scopus |
| 3 | The integrated system of ensuring sustainable development of the region | Proceedings of the 32nd International Business Information Management Association Conference, IBIMA 2018 - Vision 2020: Sustainable Economic Development and Application of Innovation Management from Regional expansion to Global Growth, pp. 3708-3714. (SCOPUS) (2019) | Web of Science |
| 4 | Introduction Of Digitalization In The Process Of Preservation Of The Historical Heritage Of Kazakh Culture // | Journal of Positive School Psychology. – 2022. - Vol. 6, No. 6. - Рр. 4012-4022. https://www.journalppw.com/index.php/jpsp/article/view/8108/5273 процентиль 81 | Scopus |
| 5 | Problems of introducing modern students to a healthy lifestyle | Journal of Positive School Psychology. – 2022. - Vol. 6, No. 7. - Рр. 2634-2643. https://journalppw.com/index.php/jpsp/article/view/11828 процентиль 81 | Scopus |
|  | О некоторых вопросах историографии военных конфликтов конца ХХ и начала ХХI веков | Военно-политический журнал «Ориентир». - № 3. – Нур-Султан, 2020. – С. 62. | ККСОН |
|  | Кахаский султан Ураз-Мухаммед- представитель кахаъской и российской военной аристократии конца XVI- начала XVII в.в | Военно-теоретический журнал «Бағдар».№ 1, 2019- С. 106-108 | ККСОН |
|  | Исторические факторы соблюдения норм обычного права в традиционном казахском обществе | Хабаршысы – Вестник НУО. - № 2, 2018. – Астана: НУО, 2018. – С. 127-130. | ККСОН |
|  | Особенности мобилизации населения в Первую мировую войну в Российской империи | ХАБАРШЫСЫ Академии военных наук. - № 2, 2018. – Астана, 2018. С. 98-104. | ККСОН |
|  | Н. Назарбаев еңбектері – қазақстанның мемлекеттік қауіпсіздігі, ынтымақтастығы мен перспективтілігінің флагманы ретінде Хабаршысы | Вестник. - № 2, 2017. – Астана: НУО, 2017. – С. 7-11. (рекомендован ККСОН) | ККСОН |
|  | Основные этапы борьбы Казахского ханства с Джунгарским ханством (середина ХVII – ХIII вв.) | Бағдар – Ориентир. - № 2, 2017. – Астана: НУО, 2017. – С. 62-64. (рекомендован ККСОН) | ККСОН |

Deputy Head for the Scientific Direction - 3D Modeling, Senior Researcher: Mukhamadeeva R.M. - Ph.D., Associate Professor of KU named after A. Myrzakhmetova, scientific and pedagogical experience is more than 30 years, there is experience in leadership work as the director of the Regional Technopark under the akimat of the North Kazakhstan region, more than 40 publications, of which 9 articles are indexed in knowledge-intensive databases (6 of them over the past 5 years) , has certificates of participation in international conferences, a certified teacher of CAD KOMPAS V18, has 3 copyright certificates, a patent for a utility model, co-author of the textbook "Drawing", has a user certificate in the 3Ds Max system. h-index: 2 (Scopus), Scopus Author ID: 57190412248; Web of Science Researcher E-8463-2016; https://orcid.org/0000-0001-7453-218X

It is assumed that her duties will include the practical implementation of bench tests, rendering, scanning and three-dimensional printing of cultural and historical objects.

Senior Researcher – U. B. Kusainova, Master of Technical Sciences, specialty 6M070300 “Information Systems”, has more than 15 scientific publications, 2 copyright certificates, confident PC user: MS Office, MS Excel, MS PowerPoint, MS Access. Knowledge of programming languages: Turbo Delphi, Pascal, Python, etc. Working with: DBMS SQL, SQLite, HTML. Has 2 publications in journals with impact factor Scopus Author ID: 57201383846; https://orcid.org/0000-0002-7221-3166  .

The duties, as the executor of the program, will include all work with digital objects, their analysis, systematization and creation of a digital archive of cultural and historical objects of North Kazakhstan.

Junior researcher - Englisova G.E., currently a master student of the educational program "History", the author of 2 publications, has experience working with museum exhibits, speaks English. It is assumed that her duties will include the maintenance of all documentation, the design of scientific reports, assistance in the systematization of digitized objects.

Another junior researcher, 1st year undergraduate Mukhamadeev Tagir Takhirovich. He has 2 publications, one specifically in the direction of the digitalization of historical objects, one monograph and experience in working with financial documents. His responsibilities will include preparation of documentation for the Project and bookkeeping.

Таблица 1 – Состав исследовательской группы

| № п/п | FULL NAME. (if any), education, degree, academic title | Main place of work, position | Hirsch index, ResearcherID, ORCID, Scopus Author ID (if available) | Role in the project or program and the nature of the work performed | Brief rationale for participation |
| --- | --- | --- | --- | --- | --- |
| 1 | Mukhamadeeeva Irina Aleksandrovna, Ph.D.. | Kokshetau University named after A. Myrzakhmetova Professor | h-index: 2 (Scopus), 0 (WOS) https://orcid.org/0000-0003-0590-0756 Researcher ID 57207822681, Web of Science: AHH-1048-2022, | Head, senior researcher | Selection of objects of cultural and historical heritage |
| 2 | Mukhamadeeeva Railya Minibulatovna, Ph.D. | Kokshetau University named after A. Myrzakhmetova, docent | h-index: 2 (Scopus), 0 (WOS) Scopus Author ID: 57190412248; Web of Science Researcher E-8463-2016; https://orcid.org/0000-0001-7453-218X | Senior Researcher | Practical implementation of bench tests, rendering, scanning and 3D printing of cultural and historical objects |
| 3 | Kusainova Ulzhan Bolatovna, Master of Science, Ph.D. | Kokshetau University named after A. Myrzakhmetova, Senior Lecturer | h-index: 1 Scopus Author ID: 57201383846; https://orcid.org/0000-0002-7221-3166 | Senior Researcher | All work with digital objects, their analysis, systematization and creation of a digital archive of cultural and historical objects of North Kazakhstan. |
| 4 | Englisova Gulzhanat Ermekovna. Master student | Kokshetau University named after A. Myrzakhmetova, undergraduate |  | Junior Research Fellow | Maintenance of all documentation, preparation of scientific reports, assistance in systematization of digitized objects |
| 5 | Mukhamadeev Tagir Takhirovich. Master student | Kokshetau University named after A. Myrzakhmetova, undergraduate |  | Junior Research Fellow | Maintaining accounting records |

Table 1.1 Publications of group members on the topic of the Project

|  | Mukhamadeyeva R.M. Development prospects of introduction of innovative technologies 3dprinting in Kazakhstan // IOP Conference Series: Materials Science and Engineering: Conference on Modern Trends in Manufacturing Technologies and Equipment 2019. – Vol. 709 (4)/ DOI 10.1088/1757-899X/709/4/044080 Cite Score - 0.7, 23. https://www.scopus.com/record/display.uri?eid=2-s2.0-85079211826&origin=resultslist&sort=plf-f |
| --- | --- |
|  | R. Mukhamadeyeva Research and development of additive technology in industrial manufacturing of new products in Kazakhstan // International journal of research. – GRANTHAALAYAH, (2019). – P. 121-133. DOI: https://doi.org/10.29121/granthaalayah.v7.i2.2019.1014 |
|  | R. Mukhamadeyeva Problems of introduction of innovative technologies 3D-printing in Kazakhstan // International Journal of Current Research. – 2017 - Vol. 9, Issue, 11. - Рp. 60443-60447. https://www.journalcra.com/sites/default/files/issue-pdf/27189.pdf |
|  | Mukhamadeyeva R.M., Nazarenko M., Okselenko O., Abayeva N., Golovachyova V., Baidak Y. Innovations in technical and natural science. 4. Аддитивные технологии в Казахстане // Innovations in technical and natural sciences: Monograph, Volume 2 / ed. by P. Busch. – Vienna: «East West» Association for Advanced Studies and Higher Education. – GmbH, 2016. – 56 p. https://er.nau.edu.ua/bitstream/NAU/25174/1/%D0%A2%D0%B5%D1%85-%D0%BC%D0%BE%D0%BD%D0%BE-4.pdf |
|  | Mukhamadeyeva R.M., Fidchenko I.K. Research of additive technology in Kazakhstan // XIII Международная конференция по научному развитию в Евразии. - Vienna, Austria 2017. - Рр. 18-20. https://www.elibrary.ru/item.asp?id=29788286 |
|  | Mukhamadeyeva R.M., Muhamadeyev T.M., Muhamadeyevа I.A. Implementation issues of additive technologies // International journal of engineering sciences & research technology. – № 5(2). – 2016. – Р. 564-568. https://ijesrt.com/issues%20pdf%20file/Archive-2016/February-2016/65_IMPLEMENTATION%20ISSUES%20OF%20ADDITIVE%20TECHNOLOGIES..pdf |
|  | Попов А.Ю., Акинов Е.К., Мухамадеева Р.М. Внедрение аддитивных технологий в производство новых изделий // Материалы Международной научно-практической онлайн конференции «Современные инженерные инновации и технологии» посвященной 30 –летию Независимости Республики Казахстан и Всемирному дню инженерии. – Кокшетау, 2021. - С. 31-35. http://www.kgu.kz/ru/konferencii-kgu-im-s-ualihanova |
|  | Мухамадеева Р.М. Quality control in additive technology // BREAKTHROUGH SCIENTIFIC RESEARCH AS AN ENGINE OF SCIENCE: Collection of articles following the results of the International Scientific and Practical Conference. - Ufa, December 06, 2021. - Sterlitamak: AMI, 2021. – Р. 5-8. https://ami.im/sbornik/MNPK-IN-10.pdf |
|  | Мейрамбек Ф.М., Кусаинова У.Б. Развитие информационных систем в Республике Казахстан // Научно практический журнал «Наука и реальность». – Омск, 2021. - №1(5). – С. 18-23. https://www.elibrary.ru/item.asp?id=44880204 |
|  | Aktayeva, A., Niyazova, R., Muradilova, G., Makatov, Y., Kusainova, U. Cognitive Computing Cybersecurity: Social Network Analysis // Communications in Computer and Information Science 3rd International Scientific Conference on Convergent Cognitive Information Technologies. – Vol. 1140. - Moscow: M.V. Lomonosov Moscow State University Press, 29 November - 2 December 2018. – Р. 28-43. ISSN 1865-0929 Cite Score 2021 - 0.9, 31. |
|  | ##### Плескачев Д.В., Кусаинова У.Б., Актаева А.У. Совершенствование методов и средств контроля знаний при помощи технологий визуализации // Вестник КТИ. Педагогическая серия. - 2020. - №3(39). - С 93-95. https://agz.edu.kz/public/uploads/OBNOVLENIE_SAITA_2015/OONIiRIR/VESTNIKI/vestnik_39.pdf |
|  | ##### Макатов Е.К., Актаева А.У., Кусаинова У.Б., Аусилова Н.М. Әлеуметтік желілер: тарих және талдау // Вестник Евразийского национального университета имени Л.Н.Гумилева. Серия «Технические науки и технологии». - 2019. - №1(126). - С 60-66. ##### https://bultech.enu.kz/article/archive/view?id=social-networks-history-and-analysis |
|  | ##### Енглисова Г.Е. Народные традиции и перспективы их сохранения в условиях глобализации // Международная научно-практическая конференця «Этническая социализация детей и молодежи в поликультурном мире: миссия институтов образования». - Курский государственный университет. - 17–18 сентября 2019 года, г. Курск. ##### https://cloud.kursksu.ru/kursksu.ru/news/2019/September/10/3K99KnnY.pdf |
|  | ##### Енглисова Г.Е.Программа «Рухани-Жанғыру» как реализация пути модернизации общественного сознания // Международнаянаучная конференция студентов и молодых ученых «ǴYLYM JÁNE BILIM – 2021». – НұрСұлтан. – 2021. - С. 4709-4711. ##### http://is.nkzu.kz/publishings/%7BFA80AEBE-9F0A-4EB1-9C3F-046AEEE20934%7D.pdf |
|  | ##### Мухамадеева И.А., Мухамадеев Т.Т. Синтез технологий, как путь реализации потенциала национальных казахских традиций Материалы ХХХVI Международной научно-практической конференции «Актуальные вопросы науки и практики» (10 июня 2021 года) - Анапа, 2021. - С. 96-101. https://innova-science.ru/arhiv-konferenczij-2021/ |
|  | ##### Мухамадеева Р.М., Мухамадеева И.А. Внедрение цифровизации в процесс сохранения национального потенциала Казахской культуры // Матрица научного познания – 2022 - №3-1 – С. 88-93. https://os-russia.com/SBORNIKI/MNP-2022-03-1.pdfhttps://os-russia.com/SBORNIKI/MNP-2022-03-1.pdf |

6. Research environment

All team members in the Project have jobs related to history and digitalization. There are joint (Mukhamadeeva I.A. and Mukhamadeeva R.M.) publications and joint intellectual property rights on the chosen subject. Each of the five members of the Project has experience in participating in competitions for innovative projects and Startups, and also has experience in presenting their developments for commercialization.

The material and technical security of the project is at a fairly high level. For the implementation of the project, it is planned to use the territory and equipment of the Kokshetau University named after Abay Myrzakhmetov.

Table 2 - Material and technical base

| № п/п | View equipment | Model and year release | Quantity available units | State (new, good, bad) |
| --- | --- | --- | --- | --- |
| 1 | Computers Intel 4, | Н16Н2-М12, 2018г. | 14 | new |
| 2 | Windows 10 Pro | 2020 г. | 14 | License option |
| 3 | САПР КОМПАС-3D V18 | 3D., 2018г. | 10 | License for 10 seats |
| 4 | 3D Printer PICASO | DESIGNER X 2021 г. | 1 | new |
| 5 | 3D- Printer Stratasys with auxiliary material removal system ObjetWaterJet | Objet 30 Prime 2015 г. | 1 | good |
| 6 | 3D Printer WANHAO | Duplicator 4, 2014 г. | 1 | good |
| 7 | Graphics editor 3Ds Max | 3Ds Max 2020 г. | 1 | License option |

The university has all the necessary communications. To accommodate the Project equipment, the Design and 3D Modeling Laboratory will be used, at the address Kokshetau, st. Auezov 178a, room 101/1 and a CAD laboratory in room 102/2. The university library is located at the same address with a connection to the electronic resource of interlibrary loan. CUAM provides training in 26 bachelor's and 13 master's specialties, which will help to receive various consulting services during the implementation of the Project and attract more young people to get acquainted with a new direction - historical informatics and new digital technologies.

7. Justification of the requested funding

The main items for financing are:

-  Payroll fund, taking into account all social taxes, which will amount to 39% of the total amount of financing;

-  Purchase of equipment for research and bench tests is 29%;

-  Scientific trips and scientific and organizational support, in the amount of no more than 5%

-  Operational costs and rental of equipment with third party services will be less than 10%.

1. The salary of scientists involved in the conduct of scientific research, taking into account all taxes and deductions, amounted to 19521.25 thousand tenge for the entire period of the project.

2. Scientific trips are associated with the collection of information and the development of new technological methods in conducting research, the reimbursement of which does not exceed the rates for reimbursement of travel expenses established by the Rules on business trips within the Republic of Kazakhstan. For the entire period 1210 thousand tenge.

For familiarization, training and advanced training when using new equipment, trips to research institutes can be planned, these costs are included in the purchase of both equipment and operating costs.

The main business trips around the region for three-dimensional scanning of objects of cultural and historical heritage can be one-day and compensated by wages.

Mandatory trips to the Autonomous Cluster Fund "Park of Innovative Technologies", twice to the city of Almaty, two employees with hotel accommodation for 3 days and a trip for 2 days there and back, will cost 440 thousand tenge per year. The budget for scientific trips is laid down in accordance with the established standards for the following indicators: the daily allowance is on average about 6,000 tenge per person per day; the cost of a railway ticket is on average 15,000 tenge per person, accommodation - 10,000 tenge.

Business trips are expected with reports and consultations 2 times a year for 2 people for 5 days, therefore, 20 average annual number of person-days = 4x5 years = 20. Considering that the first year will include only 11 months, the total amount of business trips in Kazakhstan will be 1210 thousand tenge.

Business trips outside of Kazakhstan are not planned.

3 Third party services may amount to 10,822 thousand tenge. It is planned to use the services of equipment suppliers as third-party organizations in case of possible difficulties in the operation of new equipment, as well as the services of a printing house when releasing finished products in the form of teaching aids or advertising booklets with information about 3D scanning, 3D modeling and 3D printing services. Also rent a car for trips to historical monuments for shooting and three-dimensional scanning. The services of third-party organizations will include car rental: 10 trips per month, car rental per day 20000x10=200 thousand tenge for 10 months of 2023

11 months of 2023 = 200*10=2200 thousand tenge

12 months of 2024 = 200*12=2400 thousand tenge

12 months of 2025 = 200*6=1200 thousand tenge

4. It is planned to purchase consumables for research in the amount of 1150.0 thousand tenge. This is first of all: the material that is needed for a new 3D printer, photopolymer resin, in addition, a support material for 3D printing is required, and therefore a solvent for the support material. For 3D PrinterWANHAO in CUAM Acrylonitrile Butadiene Styrene (ABS) and Polylactide (PLA) or PETG. The distribution by years of the program is accepted: in the first year, only after the acquisition of equipment, 150.0 thousand tenge is planned for consumables, the bulk of the costs for consumables will go to the second and third years and will amount to 500.0 thousand tenge.

5. A three-dimensional scanner is also necessary for the successful completion of the project; without it, a full-fledged study is impossible. it is the scanner that allows you to perform the main task of the program and, in addition, it is possible to carry out control and measurement work on printed samples. A scanner that provides the ability to scan large and small objects of cultural and historical heritage. 3D scanner EinScan Pro 2X Plus Industrial Pack + Color Pack worth 100 thousand tenge.

To print on a 3D machine, a digital file of a 3D model is needed, it can be obtained by rendering, or it can be obtained by pure scanning. At the same time, having a three-dimensional model, it can be corrected or improved, or a digital restoration can be carried out. Thus, if the scanned model is of historical value and it is required to create a duplicate of this product, it is printed on a reduced scale. It is also possible to scale geographical objects of large sizes,

Need to purchase:

Drone DJI Air 2S More Combo at a price of 700.0 thousand tenge

EinScan Pro 2X Plus 3D Scanner is the latest model of multifunctional handheld 3D scanner, priced at 1800.0t.

A printer for three-dimensional printing of a fairly accurate prototype MAGNUM RX costs 9,198,700 tenge, including delivery and installation, it can be accepted = 9,720.0 thousand tenge. The total cost of the equipment will be 8650+5220+500= 12220.0 thousand tenge.

6. During the implementation of the project, scientific and organizational support and other services will amount to 10822.0 thousand tenge, including the costs of preparing and publishing scientific abstracts and articles after the first year of work, at least two in one reporting year, in specialized publications with non-zero impact factor included in the scientometric systems - WOS, Scopus, specifically scheduled for publication in the journal "Historical Social Research", which has a percentile of 78, as well as in publications recommended by KOKSNVO and journals of the RSCI.

It will also be mandatory to participate in international conferences, the materials of which are published in journals. "New Historical Bulletin" is a Russian scientific journal of the Russian State University for the Humanities. The journal publishes only articles relating to historical issues. "Social Evolution & History" is also a fairly authoritative publication. It is possible to publish the results of using a three-dimensional scanner in the Computer Graphics and Computer-Aided journal. The journal is indexed in the Scopus and Web of Science databases. The research results are expected to be published in The Rapid Prototyping Journal, which is included in the impact factor of 3.17 for 2019-2020. The impact factor of this journal increased by 13.2% over the year, which indicates the relevance and prospects of the Project.

Registration fees for participation in international scientific and practical conferences and exhibitions, organization and holding of Seminars and Round Tables "Digitalization in historical science" to disseminate innovative technology and attract sponsors from small and medium-sized businesses. Conducting scientific and practical conferences will make it possible to disseminate the acquired new knowledge on innovative technologies.

In addition, the costs are laid down for the publication of a textbook in Russian and Kazakh languages"Digitalization in the preservation of historical monuments of Northern Kazakhstan" and the monograph "Synthesis of technologies as a way to realize national potential." 2 copyright certificates "Introduction of digitalization into the process of preserving national potential" and "Digital repository of cultural and historical objects of Northern Kazakhstan" will be issued.

7. No funds are planned to be spent on renting equipment in accordance with the objectives of the project. Based on the price of equipment for the initial production laboratory of the Kokshetau University named after Abay Myrzakhmetov, Kokshetau city.

8. Operating expenses for the maintenance of equipment and machinery used to implement the program will amount to 4,076.75 thousand tenge. Existing equipment requires constant technical support and operating costs. The costs for the development of new equipment and technical support are assumed. Contracts will be concluded with service centers for maintenance of computer equipment. The peculiarity is that the first year is costly, after a year experience is gained and a smaller number of requests for help. In addition, during the implementation of the program, regular movements around the region are planned, for this, vehicles of group members can be involved and fuel costs will be paid.

The requested amount of funding for the entire duration of the program is 50,000 thousand tenge. (fifty million tenge) and by years: 2023 - 19180 thousand. tenge, 2024 - 17500 thousand tenge, 2025 - 13320 thousand tenge.

Table 2 - Summary cost estimates for the requested program amount

| № п/п | Name of the item of expenditure | Amount of financing, tenge |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Total | 2023 (Year 1) | 2024 (Year 2) | 2025 (3rd year) |
| 1. | Salary (including taxes and other obligatory payments to the budget) | 19521250 | 6135250 | 6693000 | 6693000 |
| 2. | Business trips | 1210000 | 330000 | 440000 | 440000 |
| 3 | Scientific and organizational support, other services and works | 1210000 | 330000 | 440000 | 440000 |
| 4. | Purchase of materials (for individuals and legal entities), purchase of equipment and (or) software (for legal entities) | 1210000 | 330000 | 440000 | 440000 |
| 5. | Expenses for rent, operating expenses of equipment and machinery used for the implementation of research | 4076750 | 1520750 | 1278000 | 1278000 |
| Total |  | 50000000 | 19180000 | 17500000 | 13320000 |

Table 3 - Compensation (including taxes and other obligatory payments to the budget)

| № п/п | Позиция | Salary, tenge |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 1st year |  |  |  | 2nd year |  |  |  | 3rd year |  |  |  | Total (group 6+ group 10+ group 14) Employment (full / part-time)) |
|  |  | Employment (full / part-time)) | Salary, tenge per month | Number of months of work | Amount (group 3 × group 4 × group 5) | Employment (full / part-time)) | Salary, tenge per month | Number of months of work | Amount (group 3 × group 4 × group 5) | Employment (full / part-time)) | Salary, tenge per month | Number of months of work | Amount (group 3 × group 4 × group 5) |  |
|  |  |  |  | months |  |  |  | months |  |  |  |  | гр.13) |  |
|  |  |  |  | work |  |  |  | work |  |  |  |  |  |  |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 |
| 1. | Core Research Team Staff |  |  | х |  |  |  | х |  |  |  | х |  |  |
|  | Supervisor | complete | 150000 | 11 | 1650000 | complete | 150000 | 12 | 1800000 | complete | 150000 | 12 | 1800000 | 5250000 |
|  | Senior Research Fellow | complete | 100000 | 11 | 1100000 | complete | 100000 | 12 | 1200000 | complete | 100000 | 12 | 1200000 | 3500000 |
|  | Senior Research Fellow | complete | 100000 | 11 | 1100000 | complete | 100000 | 12 | 1200000 | complete | 100000 | 12 | 1200000 | 3500000 |
|  | Мл.научный сотрудник | complete | 75000 | 11 | 825000 | complete | 75000 | 12 | 900000 | complete | 75000 | 12 | 900000 | 2625000 |
|  | Junior Researcher | complete | 75000 | 11 | 825000 | complete | 75000 | 12 | 900000 | complete | 75000 | 12 | 900000 | 2625000 |
| 3. | Total payroll fund (column 1+column 2) | х | х | х | 5500000 |  |  |  | 6000000 |  |  |  | 6000000 | 17500000 |
| 4. | Taxes and other obligatory payments to the budget, (total column 4.1 + column 4.2 + column 4.3) | х | х | х | 635250 | 0 | 0 | 0 | 693000 | 0 | 0 | 0 | 693000 | 2021250 |
|  | Calculation of social tax expenses | х | х | х | 173250 | 0 | 0 | 0 | 189000 | 0 | 0 | 0 | 189000 | 551250 |
|  | Calculation of expenses for the payment of social contributions to the State Social Insurance Fund | х | х | х | 297000 | 0 | 0 | 0 | 324000 | 0 | 0 | 0 | 324000 | 945000 |
|  | Compulsory health insurance contributions | х | х | х | 165000 | 0 | 0 | 0 | 180000 | 0 | 0 | 0 | 180000 | 525000 |
| Total |  | х | х | х | 6135,250 | 0 | 0 | 0 | 6693000 | 0 | 0 | 0 | 6693000 | 19521250 |
| (гр.3+ гр.4) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Table 4 - Business trips within the Republic of Kazakhstan

| № | Destination (name of settlement, region) | Reimbursement rates for 1 person, tenge |  | Average annual man-days |  | Average annual number of business travelers, people | Average cost of one round trip, tenge | Total, thousand tenge gr.7× (gr.3×gr.5+ gr.4×gr.6)+ gr.7×gr.8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | per diem (2MCI) | renting a dwelling | for daily expenses | for renting a dwelling |  |  |  |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 |
| 1. | 2023 год (1-й год) |  |  |  |  |  | х |  |
| 1.1. | Алматы | 3000 | 15000 | 60000 | 100000 | 1х2х5 | 75000 | 330000 |
| 2. | 2024 год (2-й год) |  |  |  |  |  | х |  |
| 2.1. | Алматы | 6000 | 10000 | 120000 | 200000 | 2х2х5 | 30000 | 440000 |
| 3. | 2025 год (3-й год) |  |  |  |  |  | х |  |
| 3.1. | Алматы | 6000 | 10000 | 120000 | 200000 | 2х2х5 | 30000 | 440000 |

Table 5 – Scientific and organizational support, other services and works

|  | Name | unit of measurement |  | Quantity, units |  | Unit cost, tenge |  | Total cost, tenge (column 4 × colum 5) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 |  | 4 |  | 5 |  | 6 |
| 1. | 2023 (Year 1), total |  |  |  | х |  | 2544000 |  |
| 1.1. | Scientific publication indexed in Scopus | шт |  | 1 |  | 2124000 |  | 2124000 |
| 1.2. | Author's certificate and obtaining ISBN | шт |  | 1 |  | 20000 |  | 20000 |
| 2. | 2024 (year 2), total |  |  |  | х |  | 3869000 |  |
| 2.1. | Scientific publications indexed in KOKSNVO | шт |  | 2 |  | 50000 |  | 100000 |
| 2.2. | Publication of the monograph | шт |  | 1 |  | 3769000 |  | 3769000 |
| 3. | 2025 (year 3), total |  |  |  | х |  | 4409000 |  |
| 3.1. | Scientific publications indexed in KOKSNVO | шт |  | 2 |  | 125000 |  | 250000 |
| 3.2. | Scientific publication indexed in Scopus | шт |  | 1 |  | 700000 |  | 700000 |
| 3.3 | Certificate of authorship | шт |  | 1 |  | 9000 |  | 9000 |
| 3.4 | Organization and holding of the Seminar and Round Table "Digitalization in historical science" | шт |  | 2 |  | 1000000 |  | 2000000 |
| 3.5 | Publication of a textbook and guidelines for the training of young specialists in rendering, restoration, reconstruction, etc. | шт |  | 2 |  | 725000 |  | 1450000 |
| Total (group 1 + group 2 + group 3), tenge |  |  |  |  | х |  | 10822000 |  |

Table 6 - Purchase of materials, equipment and (or) software (for legal entities)

| № | Name | unit of measurement |  | Quantity, units | Cost per unit, thousand tenge | Total cost, tenge (column 4 × colum 5) |
| --- | --- | --- | --- | --- | --- | --- |
| п/п |  |  |  |  |  |  |
| 1 | 2 | 3 |  | 4 | 5 | 6 |
| 1. | 2024 (year 2), total |  |  |  | х | 8650000 |
| 1.1. | Drone DJI Air 2S More Combo | шт |  | 1 | 4 200 | 4200000 |
| 1.2. | 3D-scanner EinScan Pro 2X Plus | шт |  | 1 | 4 300 | 4300000 |
| 01.мар | Material for 3D | литр |  | 30 | 5 | 150000 |
| 2. | 2024 (year 2), total |  |  |  | х | 5220000 |
| 2.1. | 3D- Printer MAGNUM RX | шт |  | 1 | 5020 | 5020000 |
| 2.2. | Material for 3D | литр |  | 100 | 5 | 200000 |
| 3. | 2025 (year 3), total |  |  |  | х | 500000 |
| 3.1. | Material for 3D | литр |  | 100 | 5 | 500000 |
| Total (group 1 + group 2 + group 3), tenge |  |  |  |  | х | 14370000 |

Table 7 - Expenses for rent, operating costs of equipment and machinery used for the implementation of research

| № п/п | Name | unit of measurement | Unit price, tenge | Quantity, units | Total, tenge (group 4 × group 5) |
| --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 |
| 1. | 2024 (year 2), total | х | х |  | 1520750 |
| 1.1. | Car rent | месяц | 6000 | 11 | 660000 |
| 1.2. | Customer service | часы | 1000 | 860,75 | 860750 |
| 1.3 |  |  |  |  |  |
| 2. | 2024 (year 2), total | х | х |  | 1278000 |
| 2.1. | Car rent | месяц | 6000 | 12 | 720000 |
| 2.2. | Customer service | часы | 1000 | 558 | 558000 |
| 2.3 |  |  |  |  |  |
| 3. | 2025 (year 3), total | х | х |  | 1278000 |
| 3.1. | Car rent | месяц | 6000 | 12 | 720000 |
| 3.2. | Customer service | часы | 1000 | 558 | 558000 |
| 3.3 |  |  |  |  |  |
| Total (group 1 + group 2 + group 3) |  | х | х |  | 4076750 |

8. Project Implementation Plan

Table 8 - Implementation Work Plan

| № п/п | Name tasks and measures for their implementation | Deadline |  |  |  | Expected results of the project implementation (in the context of tasks and activities), form of completion |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Start (month) |  | The ending (month) |  |  |
| 2023 |  |  |  |  |  |  |
| 1 | Obtaining new data for research, digital conservation and restoration of cultural and historical heritage | 01.02. | 29.12 |  |  | Analytical reference on the state of cultural and historical objects of Northern Kazakhstan |
| 1.1 | Selection of cultural and historical objects for digitization | 01.02 | 30.08 |  |  | List of priority nearby cultural and historical objects requiring digital preservation |
| 1.2 | Creation of a list and development of a calendar plan for digitization | 01.03 | 15.12 |  |  | A clear calendar plan for the digitization of selected objects |
| 1.3 | Acquisition and approbation of the operation of a three-dimensional scanner and quadrocopter | 01.03 | 29.09 |  |  | Obtaining trial digital models of at least 2 cultural and historical objects of different sizes |
| 1.4 | Start of work on placing publications in journals with a high impact factor | 01.07 | 30.12.2024 |  |  | 1-Scientific publication of a review article with indexing in Scopus 2-Author's certificate and obtaining an ISBN for the project description |
| 2024 |  |  |  |  |  |  |
| 2 | Digitization of 8 large historical and geographical objects and 30 small cultural and historical forms | 01.02 | 30.10 |  |  | Digital models of specific objects |
| 3 | Monitoring of the state, identification of objects of historical heritage necessary for restoration in Northern Kazakhstan 3.1 Purchasing a 3D printer | 10.01 | 01.06 |  |  | Digital models of specific objects Help on the status of explored objects |
|  | Scientific and organizational activity | 01.06 | 30.12 |  |  | Scientific publications indexed in KKSON - Publication of the monograph |
| 2025 |  |  |  |  |  |  |
| 4 | Creation of a special repository on the basis of the National Museum of the Republic of Kazakhstan for the formation, replenishment and systematization of cultural and historical collections of Northern Kazakhstan | 03.06 | 30.12 |  | Virtual collection of digitized cultural and historical objects in the northern region of Kazakhstan |  |
| 5 | Scientific and organizational activity | 10.01 | 30.12 |  | - Articles in journals recommended by KKSON (from two authors) - Scientific publication indexed in Scopus (joint publication) - Certificate of authorship - Organization and holding of the Seminar and Round Table "Digitalization in historical science" - Preparation for publication of a textbook and guidelines for the training of young professionals in the rendering, restoration and reconstruction of real objects |  |

9. Expected results

Direct results:

1) A database of digitized, three-dimensional cultural and historical objects of Northern Kazakhstan will be created;

2) Scientific articles will be published, of which

- two articles in a peer-reviewed scientific publication indexed in the Scopus database and having a CiteScore percentile of at least 35 (thirty-five);

- two articles in journals recommended by the KOKSNVO;

- written and defended one master's thesis;

- one monograph with ISBN "Digital History of Northern Kazakhstan" was published;

- an author's certificate was received on the topic “Three-dimensional technologies in the process of preserving the cultural and historical heritage of Kazakhstan;

3) One international event (round table, webinar, etc.) “Digitalization in historical science” will be held;

4) Material will be collected for writing a teaching aid for the training of young specialists in rendering, restoration and reconstruction of real objects.

New knowledge will be obtained that will enrich the existing museum collections of the Northern region of Kazakhstan. The introduction of a geo-information database of monuments will enable the district authorized bodies to optimize and increase the effectiveness of measures to preserve monuments. There will be an opportunity for everyone who wants to print a three-dimensional reduced model of digitized objects from the resulting database.

Economic effect: it is possible to use digitized three-dimensional models for the manufacture of souvenirs or educational products. Also, the created database of digitally visualized cultural and historical objects of Northern Kazakhstan can become an export item for museums around the world. There is an obvious connection between the process of development of the national economy and the revival of material and traditional culture. Economic success has enabled the state to pay attention to the needs in the field of culture. In turn, the revival of a rich culture and the best traditions of an ethnic group has a beneficial effect on the further sustainable growth of the national economy. The study and preservation of the heritage of ancestors will provide an opportunity to unlock the potential of the Northern region as an additional factor in the country's economic growth. Knowledge and skills of ancestors, support of cultural bearers and creative associations will stimulate the development of a competitive cultural environment, the growth of human capital and the development of tourism.

Social effect: The new data obtained will help to preserve the knowledge and skills associated with the cultural and historical heritage. The past fills the future. The data obtained from the results of the research will become the basis for the formation of Kazakhstani patriotism, the development and preservation of the cultural code of the nation.

It also becomes possible to obtain accurate scaled copies of known geographical historical objects, which in turn makes it possible to provide the content of cultural and historical objects to visually impaired or blind people. This will allow them to get to know, study and explore historical monuments and objects, which will improve their quality of life. The effect will be to transfer the unique centuries-old knowledge and skills about the culture of the Republic of Kazakhstan to the general public.

Target consumers of the results obtained: Organizations of culture and art, education and science, government agencies and authorized bodies associated with the preservation of cultural and historical objects, the media, representatives of small and medium-sized businesses.

Bibliography

1. Message of the President to the people of Kazakhstan 2021 https://forbes.kz/process/poslanie_prezidenta_narodu_polnyiy_tekst

2. All rights reserved. Use the active link to strategy2050.kz: https://strategy2050.kz/ru/news/51190/

3. Nechaeva A. A. Preservation of collective memory and historical heritage// Regional policy in post-evolutionary Wales in the era of digitalization// International scientific conference “Digitalization of education: history, trends and prospects” (DETP 2020). Advances in the Social Sciences, Education, and Humanities Research, Volume 437, pp. 114-119.

4. A.N. Kozyrev. Digital economy and digitalization in historical retrospective. https://medium.com/cemi-ras/digital-economy-and-digitization-in-historical-retrospective-1ad034c16373

5. Abmair, T., Hertle, F., Reinkönster, M., Fröhlich, K., 2005. Ground-based laser scanning applications in cultural heritage conservation and civil engineering. 3D-Arch "Virtual reconstruction and visualization of complex architectures"

6. 3. Mukhamadeeva I.A., Mukhamadeev T.T. Synthesis of technologies as a way to realize the potential of national Kazakh traditions Proceedings of the XXXVI International Scientific and Practical Conference "Actual Issues of Science and Practice" (June 10, 2021) - Anapa, 2021. - P. 96-101. https://innova-science.ru/arhiv-konferenczij-2021/

7. Cusainova U.B. Cognitive Computing Cybersecurity: Social Network Analysis Communications in Computer and Information Science, - Vol.1140, 28 – 43 pp. 2020 ISBN 978-3-030-37435-8 OnlineISBN 978-3-030-37436-5 (Scopus, IF-0.7; procentile-31)

8. Beraldin, J.-A., Picard, M., El-Hakim, S., Godin, G., Latouche, K., Valzano, V., Bandiera, A., 2002. High resolution study of a Byzantine crypt 3D model with texture mapping: Combining range and photogrammetry data. ISPRS / CIPA Int. Workshop "Scanning to record cultural heritage" - addition or replacement of photogrammetry. Corfu, Greece.

9. Bernardini, F., Rushmeier, H., Martin, I.M., Mittleman, J., Taubin, G., 2002. Building a digital model of Michelangelo's Florentine Pieta. IEEE Computer Graphics and Applications, 22(1), pp.59-67.

10. Sequeira, V., Wohlfarth, E., Bovisio, E., Biotti, E., Goncalves, J. G., 2001. Hybrid 3D reconstruction and image-based rendering techniques for reality modeling. SPIE Vol. 4309, Videometry and optical methods for measuring three-dimensional shape, pp. 126-136.

11. Vladimirov VN Historical geoinformatics: geoinformation systems in historical research. AltGU.-Barnaul: AltGU Publishing House, 2005.-192 p.

12. Sequeira, W., Wohlfarth, E., Bovisio, E., Biotti, E., Goncalves, J. G., 2001. Hybrid 3D reconstruction and image-based rendering techniques for reality modeling. SPIE Vol. 4309, Videometry and optical methods for measuring three-dimensional shape, pp. 126-136.

13. Borodkin L.I., Garskova I.M. Informatsionnye resursy po istorii trudovykh otnoshenii v rossiiskoi promyshlennosti // Ekonomicheskaya istoriya. Review. Vypusk 12 / Red. L.I. Borodkina. M.: MGU, 2006. S.8-26.

14. Mukhamadeev T.M., Mukhamadeeva I.A. Analysis of relations between the Kazakh Khanate and the Muscovite state through the prism of the activities of Khan Taukel // Khabarshysy - Bulletin of the NUO. - No. 2.- 2016. - S. 22-27

15. Mukhamadeev T.M. Mukhamadeeva I.A. The main stages of the struggle of the Kazakh Khanate with the Dzungar Khanate (mid-XVII - XIII centuries) // Bagdar - Landmark. - 2017. - No. 2. - S. 62-64.

16. Mukhamadeeva I.A. Babaeva A.T. Urban-type settlement: analysis of the current socio-economic state and development problems // Science and Reality. Science & Reality. - 2021. - No. 1 (5). - pp. 161-165

17. Mukhamadeeva I.A., Mukhamadeev T.T. Synthesis of technologies as a way to realize the potential of national Kazakh traditions // Proceedings of the XXXVI ISPC "Actual Issues of Science and Practice" (June 10, 2021). - Anapa, 2021. - P. 96-101

18. Tomasi, Francesca. Modeling in the Digital Humanities: Conceptual Data Models and Knowledge Organization in the Cultural Heritage Domain // Historical Social Research. 2018. Supplement 31. S.170-179.

19. Lapina-Kratasyuk E. How digital media changed the approach to history // https://www.forbes.ru/mneniya-column/295707-kak-tsifrovye-media-izmenili-podkhod-k-istorii (Accessed 01.01. 2019).

20. Noiret S. Digital history: history and memory accessible to everyone // History - Electronic Scientific and Educational Journal - 2017. - V.8. – Issue 7 (61).

21. Public history today: an interview with Thomas Kavan and Serge Noiret // Okna Growth // https://okna.hse.ru/news/252262912.html (Accessed 01.01.2019)

22. Yumasheva Yu.Yu. – Documentary resources of archives, libraries and museums on the Internet // Historical informatics. - 2018. - No. 1. - P. 1-13. DOI: 10.7256/2585-7797.2018.1.25513 URL: https://nbpublish.com/library_read_article.php? id=25513

23. Yumasheva Yu.Yu. – Documentary resources of foreign archives on the Internet: electronic scientific reference apparatus (part one) // Historical informatics. - 2018. - No. 2.Юмашева Ю.Ю. – Документные ресурсы зарубежных архивов в сети Интернет: электронный научно-справочный аппарат (часть первая) // Историческая информатика. – 2018. – № 2. – С. 75-100. DOI: 10.7256/2585-7797.2018.2.26554 URL: https://nbpublish.com/library_read_article.php?id=26554

24. Yumasheva Yu.Yu. – Photo archives on the Internet: problems of presentation and study // Historical informatics. - 2019. - No. 1. - P. 8-46. DOI: 10.7256/2585-7797.2019.1.29087 URL: https://nbpublish.com/library_read_article.php?id=29087

25. Yumasheva Yu.Yu. – Review of photo collections of national archives, libraries, museums presented on the Internet // Historical informatics. - 2019. - No. 1. - P. 47-117. DOI: 10.7256/2585-7797.2019.1.29100 URL: https://nbpublish.com/library_read_article.php?id=29100

26. Mukhamadeyeva R.M. The creation of objects of the Kazakh culture with the use of additive technologies. Published online: 26 November 2020 DOI: https://doi.org/10.1051/matecconf/202032903022

27. Mukhamadeeva R.M., Mukhamadeeva I.A. The introduction of digitalization in the process of preserving the national potential of Kazakh culture // Matrix of scientific knowledge - 2022 - No. 3-1 - P. 88-93. https://os-russia.com/SBORNIKI/MNP-2022-03-1.pdfhttps://os-russia.com/SBORNIKI/MNP-2022-03-1.pdf

28. Yumasheva Yu.Yu. - "The most important of the arts" on the Internet (digitized collections of newsreels and documentaries presented online) // Historical informatics. - 2019. - No. 2. - S. 19-105. DOI: 10.7256/2585-7797.2019.2.29919 URL: https://nbpublish.com/library_read_article.php?id=29919